## Sheet1
Time | Start Date | Finish Date | Completed? | Due Date | Milestones | Task | Deliverable
|  |  |  | 2016-02-27 | Project Proposal/Wireframe
2 hours |  |  | Yes |  | x | Brainstorm Options | Brainstorm - Cloud Map
2 hours |  |  | Yes |  | x | Evaluate Alternatives (AOA) | Evaluation Criteria and Simple Analysis of Alternatives
.5 hours |  |  | Yes |  | x | Decide between Alternatives | Final Selection of Idea
.1 hours |  |  | Yes |  | x | Create github repository and local repo for proj | github repo and local repo for project
1 hour |  |  | Yes |  | x | Consider human-centric metrics for site | Documented 1-3 key performance indicators for site
2 hours |  |  | Yes |  | x | Create annotated concept sketch | Annotated Concept Sketch
1 hour |  |  | Yes |  | x | Draft Proposal and Customer Value Proposition (CVP) | Written Proposal with wireframe and CVP
|  |  |  | 2016-03-12 | Draft of HTML/CSS (no JS)
1 hour |  |  | Yes |  | x | Create site outline | Site outline tree map
.5 hour |  |  | Yes |  | x | Create file containers | File containers for CSS,images,javascript and html pages planned
4 hours | [5 empty] | Write content for each page | Content written in word or notepad
2 hours | [5 empty] | Wrap content in html | HTML files added to repo
3 hours | [5 empty] | Add CSS | CSS files added to repo
1 hour | [5 empty] | Revisit Schedule and update for JS | Timeline updated with activities for remaining milestones
1 hour |  |  |  |  | x | Review Final Page in HTML and CSS
|  |  |  | 2016-03-19 | First Draft of JS
[6 empty] | Draft Pseudo-Code for jquery | JS file marked up with pseudo code comments
[6 empty] | Jquery/JS code active in file | JS file with working code
|  |  |  | 2016-03-26 | Updated Rough Draft
|  |  |  | 2016-04-02 | Final Presentation